## Schedule
Construction Schedule | [16 empty] | Print: landscape, fits one page
Enter a start date and a duration in workdays for each task; the end date, the bars and the summary calculate. Change the chart start or the days per column to pan or zoom the Gantt.
Amber cells are yours to fill in. Everything else calculates.
Project |  |  | Chart start (Monday of column 1) | [7 empty] | Planned
Prepared by |  |  | Days per column (7 = weekly) |  |  | 7 |  |  |  |  | Complete (to % done)
Revision / date |  |  | Status date (draws the today band) | [7 empty] | Status date column
# | PHASE | TASK | START | DUR (WD) | END | % DONE | PRED # | OWNER / CREW | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
| Summary | [6 empty] | earliest start · latest finish · % (duration-weighted)
How the bars work: a column is shaded when the task overlaps the dates that column covers (its start date plus the days per column). The dark part of the bar follows % done. A red start date means the task starts before its predecessor finishes.
Free template by BuildWorkPro — buildworkpro.com/templates. Planning document, not a contract schedule: contract time and milestone dates come from your subcontract.

## Example
Construction Schedule — Example | [16 empty] | Print: landscape, fits one page
The completed example: a mechanical subcontract, June–November 2026, status as of August 31. Days per column is set to 14 so the whole job fits; set it to 7 for a weekly view.
Amber cells are yours to fill in. Everything else calculates.
Project |  | Harbor Point Medical Office — Building B | Chart start (Monday of column 1) |  |  | 2026-06-01 |  |  |  |  | Planned
Prepared by |  | Dana Whitfield, Project Manager | Days per column (7 = weekly) |  |  | 14 |  |  |  |  | Complete (to % done)
Revision / date |  | Rev 2 · updated September 3, 2026 | Status date (draws the today band) |  |  | 2026-08-31 |  |  |  |  | Status date column
# | PHASE | TASK | START | DUR (WD) | END | % DONE | PRED # | OWNER / CREW | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Mobilization | Mobilize, temp facilities & layout | 2026-06-01 | 3 |  | 100% |  | L. Herrera
2 |  | Submittals: RTUs, fixtures, duct shops | 2026-06-01 | 15 |  | 100% |  | D. Whitfield
3 | Underground | Underground sanitary & storm | 2026-06-04 | 15 |  | 100% | 1 | Crew A
4 |  | Underground inspection & backfill | 2026-06-25 | 3 |  | 100% | 3 | Crew A
5 | Rough-in | Domestic water rough-in, Level 1 | 2026-06-30 | 15 |  | 100% | 4 | Crew A
6 |  | Sanitary waste & vent rough-in, Level 1 | 2026-06-30 | 20 |  | 100% | 4 | Crew B
7 |  | Water & waste rough-in, Level 2 | 2026-07-28 | 20 |  | 100% | 6 | Crew B
8 | HVAC equipment | RTU curbs & roof coord. (CO-001 RTU-2) | 2026-07-06 | 5 |  | 100% | 2 | Sheet metal
9 |  | Crane day: set RTU-1 to RTU-4 | 2026-08-03 | 2 |  | 100% | 8 | Sheet metal
10 |  | Set AHU-3 & mech room equipment | 2026-08-05 | 5 |  | 100% | 9 | Sheet metal
11 | Ductwork | Duct mains & risers, Level 1 | 2026-07-13 | 20 |  | 100% | 2 | Sheet metal
12 |  | Duct mains & branches, Level 2 | 2026-08-10 | 25 |  | 65% | 11 | Sheet metal
13 |  | Diffusers, grilles & dampers | 2026-09-21 | 15 |  | 0% | 12 | Sheet metal
14 | Piping | Refrigerant piping to RTUs | 2026-08-10 | 10 |  | 100% | 9 | Crew B
15 |  | Hydronic piping, AHU-3 & reheat coils | 2026-08-17 | 20 |  | 55% | 10 | Crew B
16 | Controls | Controls rough-in & wiring | 2026-09-14 | 15 |  | 0% | 12 | BMS sub
17 |  | BMS integration & point-to-point | 2026-10-12 | 15 |  | 0% | 16 | BMS sub
18 | Insulation | Duct insulation | 2026-09-14 | 15 |  | 0% | 12 | Insulation sub
19 |  | Pipe insulation | 2026-09-21 | 15 |  | 0% | 15 | Insulation sub
20 | Fixtures | Plumbing fixtures & trim | 2026-10-05 | 15 |  | 0% | 7 | Crew A
21 | Test & balance | Testing, air & water balancing | 2026-11-02 | 10 |  | 0% | 17 | TAB agency
22 |  | Commissioning & owner training | 2026-11-16 | 3 |  | 0% | 21 | D. Whitfield
23 | Closeout | Punch list, O&M manuals, closeout | 2026-11-09 | 8 |  | 0% | 20 | L. Herrera
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
| Summary | [6 empty] | earliest start · latest finish · % (duration-weighted)
How the bars work: a column is shaded when the task overlaps the dates that column covers (its start date plus the days per column). The dark part of the bar follows % done. A red start date means the task starts before its predecessor finishes.
Free template by BuildWorkPro — buildworkpro.com/templates. Planning document, not a contract schedule: contract time and milestone dates come from your subcontract.

## How to Use
How to use the Construction Schedule Template
1. | On the Schedule sheet, enter the project, the Monday you want column 1 to start on, and the days per column: 7 gives a 16-week weekly view, 14 covers eight months at two weeks per column.
2. | List the work one task per row, grouped by phase. Give each task a start date and a duration in workdays — the end date is computed with WORKDAY, so weekends are skipped automatically.
3. | Put the task number that must finish first in Pred #. If a start date turns red, that task starts before its predecessor ends — move it or shorten the predecessor.
4. | The Gantt shades itself: light blue where a task overlaps a column, dark blue for the portion that is done as you update % done each week.
5. | Enter a status date to draw a highlighted column through the chart, then print (landscape, one page) for the trailer wall or the weekly meeting. Change the chart start date to pan forward as the job progresses.
6. | The Example sheet holds a complete six-month mechanical schedule with the same formulas — copy rows from it or clear it and use it as a second project.
TIPS FROM THE FIELD
• | Task durations of two days to two weeks are the useful range. Finer and you are maintaining a spreadsheet instead of building; coarser and slippage hides inside long bars.
• | Update % done and the status date every week, on the same day. A schedule that is updated irregularly gets ignored.
• | When a change order adds contract time, add the days to the affected task and note the CO number in the task name — the revised completion date has to match the signed change order.
• | Record delays in the daily report the day they happen. The schedule shows the effect; the daily report proves the cause.
In BuildWorkPro, phases and tasks carry start dates and workday durations, dependencies highlight the critical path, and the Gantt chart is rescheduled by dragging bars — on the same project as your change orders, site logs and pay applications.
https://buildworkpro.com/features/project-management/
Free template by BuildWorkPro — https://buildworkpro.com/templates/. Free to use and share for your own business. Not legal, accounting or engineering advice.